## Process Report Flow
Process Report Flow
Sub-activities | SBU | Generic | Specification | Therapeutic Class | Strength | Dosage Form | Product Category | Unit Forecast (Y-1) | Value Forecast (Y-1) | Launching Date | Generic Code | Product Code | PP Raised | Plant | PP Approval | Duration (PP to PP Approval) | Product Brief (PB) Sharing to R&D | 6M Forecast Sharing to R&D | Product Brief Approval | Dev RM specification to SCM by R&D | Dev RM Received | Method Dev. & Stability Initiation | 3M Stability Completion | Recipe Submission to RA | Duration (PP Approval to Recipe Submission) | Recipe Approval | DTL shared to RA by R&D | PM Spec. Shared to SMD by R&D | Tooling/ Machine/ Change parts PR to SCM by R&D/Eng | RM/PM requisition to SCM by R&D | DTL Approval | Brand Name & PM Design to RA | Duration (PM Spec Sharing to PM Design to RA) | Price Submission to RA | 6M Stability Completion | Annexure Documents to RA by R&D | Tooling/ Machine/ Change parts Availability at Plant | Brand Name & PM Design Approval | Annexure Approval | Inclusion Approval | PM Design Delivery to Vendor by SCM | AFPC Shared to QC | Commercial RM Receival | Commercial PM Receival | Technology Transfer | Duration (Annexure Approval to Commercial PM Received) | Price Approval | Finished Product Released | MA Certificate Receival | Product Launching | Duration (PP Approval to Product Launching) | PP Creator | Remarks
Demo Information | Pharma Common | Lacosamide | INN | Antiepileptic | 50mg | Tablet | New Molecule |  |  | 01.04.27 | NP07260001 | NP07260001 (a) | 07.01.2025 | NG | 01.01.26 | 34 | 12.03.2025 | 14.03.2025 | 12.03.2025 | Date | 09.03.2025 | 25.04.2025 |  | 07.08.2025 | 175 | 25.09.2025 | Date/NA | 01.10.2025 | Date/NA | Date | Date/NA | 20.09.2025 | 05.10.2025 | 10.10.2025 |  | Date | Date/NA | 15.10.2025 | 10.11.2025 |  | 30.11.2025 | 30.11.2025 | 20.12.2025 | 15.12.2025 |  | 34 | 25.11.2025 |  | 10.01.2026 | 01.02.2026 | 68 | Saif Ahmed | Due to high cost SCM couldn't manage Dev RM yet
Responsible Departments |  | PP | PP | PP | PP | PP | PP | PP | PP | PP | PP | PP | PP | PP | PP | Formula | MKT | MKT | R&D | R&D | R&D | R&D | R&D | R&D | Formula | RA | R&D | R&D | R&D/ Eng. | R&D | RA | MKT | Formula | MKT | R&D | R&D | R&D | RA | RA | RA | SCM | MKT | R&D | R&D | R&D | Formula | RA | QC | RA | MKT | Formula | MKT | SCM
Current Documentation Status | [16 empty] | Manual | Manual | Manual | Online | Online | Manual | Manual | Manual |  | Manual | Manual | Manual | Online | Manual | Manual | Manual |  | Manual | Manual | Manual | Online | Manual | Manual | Manual | Manual | Manual | Online | Online | Manual |  | Manual | Online | Manual | Manual
NPD Folder Name | [16 empty] | Internal Product Brief | 6M Forecast | Product Brief Approval | Dev. RM Spec. | Dev RM Receival | Formulation Concurrence | 3M Stability | Recipe Doc |  | Recipe Approval | DTL Doc | PM Spec. | Change Parts PR | RM Req. by R&D PM Req. by R&D | DTL Approval | Internal Brand Name Packaging Concurrence |  | Internal Price | 6M Stability | Annexure Doc | Change Parts Receival | PM Design Approval | Annexure Approval | Inclusion Approval | Hand Over Note | AFPC Doc | RM Receival | PM Receival | Technology Doc |  | Price Approval | Internal Price Circular | MA Certificate | Launching Circular
Gantt Chart Timeline | [16 empty] | 80 |  |  |  |  | 90 | 90 | 90 | [11 empty] | 90 | [11 empty] | 22 | 15

## Mail Notification
Concerned Persons | PP | PP Creator
| R&D (NG) | Raihana Begum | Senior Manager | R&D | raihana@aci-bd.com
|  | Sinthia Hossain | Deputy General Manager | R&D | sinthia@aci-bd.com
|  | Mst. Jasmin Akter | Deputy Product Development Manager | R&D | jasmin@aci-bd.com
|  | Tufikul Islam | Senior Assistant Manager | R&D | tufikul@aci-bd.com
|  | Md. Monirujjaman | Assistant Manager | R&D | monirujjaman@aci-bd.com
| R&D (AHL) | Md. Jamal Hossain | Deputy General Manager | R&D | jamal.hossain@acihealthcare.net
|  | Morsheda Akter | Assistant Manager | R&D | morsheda.akter@acihealthcare.net
|  | Mohammad Omar Faruk Patoary | Senior Assistant Manager | Validation & LCM | omar.faruk@acihealthcare.net
| RA | AKM Sharif Masud | Senior Assistant Manager | Regulatory Affairs | sharifmasud@aci-bd.com
|  | Raisul Islam Imon | Executive | Regulatory Affairs | raisul.imon@aci-bd.com
| SCM | Golam Mohammed Shahariar | Senior Manager | SCM | Shahariar.golam@aci-bd.com
|  | Ms. Laboni Saha | Senior Executive | SCM | laboni.saha@aci-bd.com
| Production (NG) | Alak Kumar Barua | Assistant General Manager | QA | alak@aci-bd.com
| QA (AHL) | Sharmin Akter (AM, QA) | Senior Executive | Warehouse | akter.sharmin@acihealthcare.net

## Gantt Chart Timeline
Product Launching Gantt Chart
|  | Total Days: | 477
Sl. No. | Item | Responsibility | Days Required
1 | Product Proposal Approval | COO sir | Approved Date
2 | Approved Dev RM Received | R&D | 80
3 | Method Dev. & Stability Initiation | R&D | 90
4 | 03M Stability Completion | R&D | 90
5 | 6M Stability Completion | R&D | 90
6 | Annexure & Price Approval | RA | 90
7 | Finished Product release | QA | 22
8 | Product Launching | MKT | 15

## Gantt Chart
Launching Timeline
[54 empty] | Standard Timeline | [6 empty] | Deviated Timeline
Manufacturing Plan of Ceftazidime+ Avibactam | [53 empty] | 24.04.2027
|  |  |  | January'26 |  |  |  | February'26 |  |  |  | March'26 |  |  |  | April'26 |  |  |  | May'26 |  |  |  | June'26 |  |  |  | July'26 |  |  |  | August'26 |  |  |  | September'26 |  |  |  | October'26 |  |  |  | November'26 |  |  |  | December'26 |  |  |  | January'27 |  |  |  | February'27 |  |  |  | March'27 |  |  |  | April'27
Item | Responsibility | Status | Days Required | W-1 | W-2 | W-3 | W-4 | W-1 | W-2 | W-3 | W-4 | W-1 | W-2 | W-3 | W-4 | W-1 | W-2 | W-3 | W-4 | W-1 | W-2 | W-3 | W-4 | W-1 | W-2 | W-3 | W-4 | W-1 | W-2 | W-3 | W-4 | W-1 | W-2 | W-3 | W-4 | W-1 | W-2 | W-3 | W-4 | W-1 | W-2 | W-3 | W-4 | W-1 | W-2 | W-3 | W-4 | W-1 | W-2 | W-3 | W-4 | W-1 | W-2 | W-3 | W-4 | W-1 | W-2 | W-3 | W-4 | W-1 | W-2 | W-3 | W-4 | W-1 | W-2 | W-3 | W-4
Product Proposal Approval | COO sir | Done | 01.01.2026
Approved Dev RM Received | R&D | Mid March | 80 | bar: January'26 W-1 to March'26 W-3
Method Dev. & Stability Initiation | R&D | Mid June | 90 | bar: March'26 W-4 to June'26 W-3
03M Stability Completion | R&D | Mid Sep'26 | 90 | bar: June'26 W-4 to September'26 W-3
6M Stability Completion | R&D | Mid Decr'26 | 90 | bar: June'26 W-4 to December'26 W-3
Annexure & Price Approval | RA | Mid Mar'27 | 90 | bar: December'26 W-4 to March'27 W-3
Finished Product release | QA | Mid Apr'27 | 22 | bar: March'27 W-4 to April'27 W-2
Product Launching | SMD | End Apr'27 | 15 | bar: April'27 W-3 to April'27 W-4

## Report Vertical
477
Sl. No. | Items | Timeline | Departments | Current Status | Upload | Days Count
1 | SBU | Pharma Common
2 | Generic | Lacosamide | PP
3 | Specification | INN
4 | Therapeutic Class | Antiepileptic | PP
5 | Strength | 50mg | PP
6 | Dosage Form | Tablet | PP
7 | Product Category | New Molecule | PP
8 | Unit Forecast (Y-1) |  | PP
9 | Value Forecast (Y-1) |  | PP
10 | Launching Date | 01.04.27 | PP
11 | Molecule Code | NP-0726-0001 | PP
12 | Product Code | NP-0726-0001 (a) | PP
13 | PP Raised | 07.01.2025 | PP
14 | Plant | NG | PP
15 | PP Approval | 01.01.26 | PP
16 | Duration (PP to PP Approval) | 34 | Formula
17 | Product Brief (PB) Sharing to R&D | 12.03.2025 | MKT | Manual | Internal Product Brief | 80
18 | 6M Forecast Sharing to R&D | 14.03.2025 | MKT | Manual | 6M Forecast
19 | Product Brief Approval | 12.03.2025 | R&D | Manual | Product Brief Approval
20 | Dev RM specification to SCM by R&D | Date | R&D | Online | Dev. RM Spec.
21 | Dev RM Received | 09.03.2025 | R&D | Online | Dev RM Receival
22 | Method Dev. & Stability Initiation | 25.04.2025 | R&D | Manual | Formulation Concurrence | 90
23 | 3M Stability Completion |  | R&D | Manual | 3M Stability | 90
24 | Recipe Submission to RA | 07.08.2025 | R&D | Manual | Recipe Doc | 90
25 | Duration (PP Approval to Recipe Submission) | 175 | Formula
26 | Recipe Approval | 25.09.2025 | RA | Manual | Recipe Approval
27 | DTL shared to RA by R&D | Date/NA | R&D | Manual | DTL Doc
28 | PM Spec. Shared to SMD by R&D | 01.10.2025 | R&D | Manual | PM Spec.
29 | Tooling/ Machine/ Change parts PR to SCM by R&D/Eng | Date/NA | R&D/ Eng. | Online | Change Parts PR
30 | RM/PM requisition to SCM by R&D | Date | R&D | Manual | RM Req. by R&D PM Req. by R&D
31 | DTL Approval | Date/NA | RA | Manual | DTL Approval
32 | Brand Name & PM Design to RA | 20.09.2025 | MKT | Manual | Internal Brand Name Packaging Concurrence
33 | Duration (PM Spec Sharing to PM Design to RA) | 05.10.2025 | Formula
34 | Price Submission to RA | 10.10.2025 | MKT | Manual | Internal Price
35 | 6M Stability Completion |  | R&D | Manual | 6M Stability
36 | Annexure Documents to RA by R&D | Date | R&D | Manual | Annexure Doc | 90
37 | Tooling/ Machine/ Change parts Availability at Plant | Date/NA | R&D | Online | Change Parts Receival
38 | Brand Name & PM Design Approval | 15.10.2025 | RA | Manual | PM Design Approval
39 | Annexure Approval | 10.11.2025 | RA | Manual | Annexure Approval
40 | Inclusion Approval |  | RA | Manual | Inclusion Approval
41 | PM Design Delivery to Vendor by SCM | 30.11.2025 | SCM | Manual | Hand Over Note
42 | AFPC Shared to QC | 30.11.2025 | MKT | Manual | AFPC Doc
43 | Commercial RM Receival | 20.12.2025 | R&D | Online | RM Receival
44 | Commercial PM Receival | 15.12.2025 | R&D | Online | PM Receival
45 | Technology Transfer |  | R&D | Manual | Technology Doc
46 | Duration (Annexure Approval to Commercial PM Received) | 34 | Formula
47 | Price Approval | 25.11.2025 | RA | Manual | Price Approval
48 | Finished Product Released |  | QC | Online | Internal Price Circular | 22
49 | MA Certificate Receival | 10.01.2026 | RA | Manual | MA Certificate | 15
50 | Product Launching | 01.02.2026 | MKT | Manual | Launching Circular
51 | Duration (PP Approval to Product Launching) | 68 | Formula
52 | PP Creator | Saif Ahmed | MKT
53 | Remarks | Due to high cost SCM couldn't manage Dev RM yet | SCM

## Comment
Departments | Items | Upload Document | Date | Remarks
MKT | Product Brief (PB) Sharing to R&D | Internal Product Brief | 12.02.26 | Waiting for originator product
| 6M Forecast Sharing to R&D | 6M Forecast | 15.02.26 | Waiting for COO Sir's approval
| Brand Name & PM Design to RA | Internal Brand Name Packaging Concurrence
| Price Submission to RA | Internal Price
| AFPC Shared to QC | AFPC Doc
| Product Launching | Launching Circular
R&D | Product Brief Approval | Product Brief Approval
| Dev RM specification to SCM by R&D | Dev. RM Spec.
| Dev RM Received | Dev RM Receival | 10.05.26 | SCM Couldn't manage DEV RM yet
|  |  | 26.05.26 | Due to high cost SCM couldn't manage Dev RM yet
| Method Dev. & Stability Initiation | Formulation Concurrence
| 3M Stability Completion | 3M Stability
| Recipe Submission to RA | Recipe Doc
| DTL shared to RA by R&D | DTL Doc
| PM Spec. Shared to MKT by R&D | PM Spec. | 10.07.26 | Need spec. correction
| Tooling/ Machine/ Change parts PR to SCM by R&D/Eng | Change Parts PR
| RM/PM requisition to SCM by R&D | RM Req. by R&D PM Req. by R&D
| 6M Stability Completion | 6M Stability
| Annexure Documents to RA by R&D | Annexure Doc
| Tooling/ Machine/ Change parts Availability at Plant | Change Parts Receival
| Commercial RM Receival | RM Receival
| Commercial PM Receival | PM Receival
| Technology Transfer | Technology Doc
RA | Recipe Approval
DTL Approval
Brand Name & PM Design Approval
| Annexure Approval | Recipe Letter by DA
| Inclusion Approval | DTL Approval by DA
| Price Approval | Approved PM Design by DA
| MA Certificate Receival | Approved Annexure by DA
SCM | PM Design Delivery to Vendor by SCM | Hand Over Note
QC | Finished Product Released | Internal Price Circular